# Marketing-in-a-Box (Owned Media)

Pipeline Execution App

Project Management Plan

| Field | Value |
| --- | --- |
| Document owner | Aditya |
| Version | 1.1 |
| Date | August 7, 2026 |
| Status | Draft — for stakeholder review |
| Companion document | Marketing-in-a-Box (Owned Media) Pipeline Execution App — Product Requirements Document (PRD) |

# 1. Project Summary

This project builds an internal application that automates the sequential generation of all 16 Phase 1 marketing assets for any client, using a dependency-aware execution engine, Claude for content generation, and a mandatory human review gate at every stage. The interface is chat-styled but purpose-built for pipeline review, not general conversation. The build is carried out by a single developer. Full functional detail is in the companion PRD; this document covers responsibilities, an MVP-first timeline, task breakdown, and risk.

# 2. Team & Roles

The build is carried out by a single developer, supported by a product owner and a strategist/reviewer. Responsibilities are listed below.

Responsibility

Requirements, prioritization, and stakeholder communication (Aditya)

End-to-end development: orchestrator, LLM executor, context store, rendering/export, and the chat-style HITL interface — built by a single developer

Approves, edits, or rejects generated assets during live runs (strategist / reviewer)

End-to-end testing across all 16 assets

# 3. Project Timeline

This project is built by a single developer. The plan below defines a minimum-viable release (MVP) achievable in 2 weeks (10 working days), followed by a post-MVP roadmap that completes full production readiness, including Phase 2.

## MVP timeline — single developer, 10 working days (2 weeks minimum)

| Day | Work | Deliverable |
| --- | --- | --- |
| 1 | Load and finalize the asset registry; set up the Postgres schema | Registry and database ready |
| 2–3 | Build the dependency resolver and idempotent run-state machine | Orchestrator can compute a valid execution order |
| 4–6 | Build the LLM executor: prompt engine, Claude integration, schema validation, pause-and-warn gate | Single-asset generation works end-to-end with validation |
| 7–8 | Build the basic chat-style HITL UI: stage timeline, draft view, approve/reject controls | Strategist can review and approve a generated draft |
| 9 | Wire in the CRO sub-pipeline (basic version) | CRO asset produces a validated draft |
| 10 | Run all 16 assets end-to-end for one sample client; export approved outputs manually | Working MVP — the full pipeline runs for a real client |

## Post-MVP roadmap — single developer, ~19 additional working days (~4 weeks)

| Phase | Work | Deliverable | Days |
| --- | --- | --- | --- |
| 1 | CRO sub-pipeline refinement and competitor scraping polish | Fully validated 4-step CRO sub-pipeline | 3 |
| 2 | Automated rendering and export: Markdown/HTML/Word, upload to SharePoint or an alternative such as Google Drive/OneDrive | Approved assets export automatically | 4 |
| 3 | Audit trail and resumability polish | Auditable, resumable runs | 3 |
| 4 | Full regression testing and bug fixing across all 16 assets | Stable, tested pipeline | 3 |
| 5 | Phase 2 (remarketing funnel) implementation — see PRD Section 15 | Remarketing assets run through the same engine | 4 |
| 6 | Deployment and documentation | Deployed system, handoff docs | 2 |

Total: approximately 29 working days (about 6 weeks) for a single developer to reach full production readiness including Phase 2, with a working MVP available after the first 10 days (2 weeks).

# 4. Milestones

| Milestone | Marks completion of | Target day |
| --- | --- | --- |
| M1 — MVP complete | Full 16-asset pipeline runs end-to-end for one client | Day 10 |
| M2 — Export automation & CRO polish complete | Post-MVP Phases 1–2 | Day 17 |
| M3 — Audit, resumability & testing complete | Post-MVP Phases 3–4 | Day 23 |
| M4 — Phase 2 implemented | Post-MVP Phase 5 | Day 27 |
| M5 — Production deployment | Post-MVP Phase 6 | Day 29 |

# 5. Detailed Task Breakdown — Post-MVP

The MVP's day-by-day tasks are listed in the timeline table above. The breakdown below expands each post-MVP phase.

## Phase 1 — CRO sub-pipeline refinement (3 days)

- Strengthen competitor scraping reliability — 1 day

- Refine the CRO audit generation step — 1 day

- Polish the Part 1 rewrite and Part 2 draft steps, with validation — 1 day

## Phase 2 — Rendering & export automation (4 days)

- Markdown / HTML / Word renderers — 2 days

- SharePoint (or Google Drive/OneDrive) upload integration — 2 days

## Phase 3 — Audit trail & resumability (3 days)

- Audit trail UI and log — 1 day

- Resumability testing and fixes — 1 day

- Run history view — 1 day

## Phase 4 — Testing (3 days)

- End-to-end regression run across all 16 assets — 1.5 days

- Bug fixing and edge cases, including the rejection loop — 1.5 days

## Phase 5 — Phase 2 (remarketing funnel) implementation (4 days)

- Add Phase 2 asset registry entries and prompt recipes — 1.5 days

- Implement the “Phase 1 complete + pixel data confirmed” gating condition — 1 day

- Extend the stage timeline UI to include Phase 2 stages — 1 day

- End-to-end test of one Phase 2 asset — 0.5 day

## Phase 6 — Deployment (2 days)

- Deployment setup — 1 day

- Documentation and handoff — 1 day

# 6. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| LLM output repeatedly fails schema validation for a given asset | Medium | Medium | Iterate the prompt recipe; strengthen the schema guard; allow strategist manual override |
| SharePoint (or the chosen alternative) integration friction (auth, permissions) | Medium | Medium | Prototype the integration early in Post-MVP Phase 2; fall back to Google Drive/OneDrive or S3/Blob if blocked |
| Scope creep: Phase 2 work starting before the MVP and core post-MVP phases are stable | Low | Medium | Phase 2 is explicitly sequenced after Post-MVP Phases 1–4 in the roadmap |
| Single developer is a bottleneck across all phases | Medium | High | MVP-first sequencing surfaces integration risks early; consider adding a second developer for post-MVP phases if the timeline slips |
| Single reviewer becomes a bottleneck across sequential approval gates | Medium | Medium | Consider allowing parallel review of independent DAG branches in a later version |

# 7. Dependencies & Blockers

- SharePoint (or the chosen alternative's) API access and credentials must be available before Post-MVP Phase 2 (rendering & export automation).

- Anthropic API access (Claude) must be provisioned before MVP Day 4, when LLM executor work begins.

# 8. Communication Cadence

- Weekly status check-in with stakeholders.

- A short demo/review at the end of the MVP and at the end of each post-MVP phase.

# 9. Definition of Done

## MVP

- All 16 assets can be generated end-to-end for one sample client through the approval gates, with manual export of final files.

- The strategist can approve, edit, or reject each draft through the chat UI.

- A failed or empty generation halts downstream execution with a visible warning.

## Full release

- Every approved output is stored in the context store and exported automatically to SharePoint (or the chosen alternative) in the correct formats.

- The audit log captures every approval decision, its reviewer, and any edits made.

- A run can be paused and resumed without data loss.

- Phase 2 (remarketing) assets run successfully through the same engine for a client with confirmed retargeting pixel data.